ECM3401 Project Logbook

Student Name: Edward Blewitt

Project Name: “LF-7T-CycleGAN: An Unsupervised Approach for 7

Tesla-Like MRI Reconstruction from 0.3 Tesla Scans

with Uncertainty Quantification”

Internal Supervisor: Dr. Ahmed Karam Eldaly

External Supervisor: N/A

Log of Activities

| Date | Key activities | Outcomes | Comments/Action plans |
| --- | --- | --- | --- |
| Term 1: Week 3 6th October - 12th October 2025 | - Started initial reading on low-field MRI IQT and developed a short reading list to gain an understanding of the research area. - Read through the foundational IQT paper by Alexander et al. - Met with supervisor in group meeting and presented progress. | - Built an initial reading list of four key papers spanning random forests, low-field epilepsy IQT, 3D conditional diffusion and alternative learning paradigms. | - Need to establish how methods are compared and what are currently the highest performing methodologies. |
| Term 1: Week 4 13th October - 19th October 2025 | - Read through initial reading list to gain basic understanding of existing literature in the field. - Met with supervisor in group meeting and presented progress. | - Became familiar with the various methods that have been applied to low-field MRI enhancement. - Started building a planning document for the literature review which includes summaries of papers which I have read through. | - Need to gain a better understanding of how MRI machines function from a physics perspective. |
| Term 1: Week 5 20th October - 26th October 2025 | - Studied the physics of MRI scanning, including proton alignment, signal detection and spatial reconstruction. - Continued reading and summarising various enhancement techniques - Met with supervisor in group meeting and presented progress. | - Improved my understanding of the relevant literature review through an in-depth comprehension of MRI physics. | - Paper was recommended to me by my supervisor. I will read this during the next week. |
| Term 1: Week 6 27th October - 2nd November 2025 | - Started writing introduction section of literature review and essay plan. - Read more academic papers on low-field MRI improvement. - Visited one of the earliest MRI scanners in the science museum - Met with supervisor in group meeting and presented progress. | - Introduction section of literature review is almost complete. | - I feel that my understanding of the field has improved a lot. I find that I understand new enhancement methods in the literature much quicker than earlier in the term. |
| Term 1: Week 7 3rd November - 9th November 2025 | - Continued writing literature review. - Full essay plan finalised. - Continued reading academic literature. - Met with supervisor in group meeting and presented progress. | - Literature review introduction section complete. - Work has been started on various methodology sections of the literature review. | - Need to decide on a baseline approach to build upon for my project. |
| Term 1: Week 8 10th November -16th November 2025 | - Finished writing literature review. - Finalised proposed project, including methodology, goals and timeline. - Started to analyse proposed project datasets. - Met with supervisor in group meeting and presented progress. | - Project proposal is complete - Literature review is complete | - Need to start work on implementing the proposed method by Tanno et al. |
| Christmas Holiday | - Changed project plan to use a different method than initial project proposal. - Started implementing project methodology and planning approach - Reached out to authors of baseline method and their university for access to code - Analysed the 7T and 0.3T datasets proposed for use in my project. - Met with supervisor in group meeting at the end of the holidays and presented progress. | - After review of the HCP and M4Raw dataset, FLAIR MRI improvement will not be possible as it is not included in the HCP repository at 7T field strength. My research will therefore focus on T1w and T2w sequences. |  |
| Term 2: Week 1 5th January - 11th January 2026 | - Began implementation of changes to CycleGAN as original authors did not respond. - Met with supervisor in group meeting and presented progress. | - Attention block implementation is complete. - Content adversarial loss implementation is complete. | - Re-implementing the recently published method is very difficult since the diagram included in the paper is ambiguous in the stride values used in the edge block. |
| Term 2: Week 2 12th January – 18th January 2026 | - Completed changes to CycleGAN by finishing the edge block, perceptual loss, and custom generator implementations. - Started first training run on limited dataset. - Met with supervisor in group meeting and presented progress. | - Model has implemented all features suggested in the reference paper. | - I think training should use .npy files rather than .png images. I will need to implement this. |
| Term 2: Week 3 19th January – 25th January 2026 | - Downloaded 1.6TB of training data from HCP and M4Raw. - Started developing pre-processing pipeline. - Met with supervisor in group meeting and presented progress. | - Full dataset was downloaded and stored on a NAS device at my home. - Pre-processing pipeline for M4Raw scans completed. Does not yet save as .npy files. | - Pre-processing HCP scans is proving difficult due to their large file size and problems with the temp directory in Windows 10. Need to move to an in-memory approach. - Transferring the full dataset via the VPN for pre-processing will take multiple weeks. I need to physically move the data. - CycleGAN will require further adaptation to handle .npy inputs. |
| Term 2: Week 4 26th January – 1st February 2026 | - Re-processing pipeline completed. - Moved three computers with dedicated GPUs and sufficient storage space to Exeter. - First full training run complete on reduced dataset. - Started manual parameter optimisation. - Added custom dataset class to handle .npy files. - Fixed a small bug in the perceptual loss. - Met with supervisor in group meeting and presented progress. | - Computers are set up and ready for training in Exeter. - Results from test training run are promising, showing clear quality transfer. - Perceptual loss component is now error-free. | - Model parameters need to be optimised before investing into training a full ensemble as this full training process will likely take a significant amount of time. |
| Term 2: Week 5 2nd February – 8th February 2026 | - Wrote script for automated parameter optimisation using Bayesian inference to reduce time. - Ran parameter optimisation. - Met with supervisor in group meeting and presented progress. | - Optimal set of hyperparameters found. - Full-model training is now ready. | - Uncertainty quantification will need to be implemented next. My supervisor has suggested using deep ensembles. |
| Term 2: Week 6 9th February – 15th February 2026 | - Started writing final report introduction section. - Began training T1w ensemble. - Met with supervisor in group meeting and presented progress. | - Final report introduction almost complete. - T1w ensemble training is almost complete. | - Need to adapt the test.py file to run inference on all ensemble members and compute uncertainty. |
| Term 2: Week 7 16th February – 22nd February 2026 | - Finished adaptations to test.py file. - Started training T2w ensemble. - Completed T1w ensemble training. - Started writing final report related work section. - Ran inference on the T1w ensemble. - Met with supervisor in group meeting and presented progress. | - Ensemble inference can now be run. Results are output as mean prediction of all members and uncertainty is computed by measuring member disagreement. - Test script maintains functionality for testing single models. - Related work section is around halfway complete. - Results from the T1w ensemble look very strong. | - Started using WandB to view training runs on multiple servers in one place. This helps me know when runs have finished earlier to reduce wasted time when training is not happening. - Need to design an overall structure for my final report. |
| Term 2: Week 8 23rd February – 1st March 2026 | - Designed layout of the poster for this project. - Produced plan for final report structure. - Met with supervisor in group meeting and presented progress. | - Poster layout is complete. - Final report structure is complete. | - Since paired training data is not available, I may need to have my results reviewed by a radiologist to prove that my model can perform well. |
| Term 2: Week 9 2nd March – 8th March 2026 | - Finished working on poster. - Reached out to Robert from the medical imaging department at the university for help. - Met with supervisor in group meeting and presented progress. | - Poster is complete, although results are preliminary due to time constraints. - Requested help in reviewing my results from the medical imaging team. | - Meeting booked with Robert from the medical imaging team to discuss how he can help. |
| Term 2: Week 10 9th March – 15th March 2026 | - Trained baseline un-modified CycleGAN implementations in the T1w and T2w contrasts. - Started working on an MRI survey. - Met with supervisor in group meeting and presented progress. | - Baseline CycleGAN models are trained for comparison. | - MRI survey is proving difficult to develop since I have needed to build it from scratch - Need to write code to compute quantitative metrics from results, although these should be heavily caveated in the report. |
| Term 2: Week 11 16th March – 22nd March 2026 | - Finished work on the MRI survey software, including an admin dashboard to view results. - Tested MRI survey software with a full run-through. - Met with supervisor in group meeting and presented progress. | - MRI survey is ready but awaiting a third model for comparison. | - Before the MRI survey can be used, I want to baseline my model against more than one other method. Unfortunately, this will not be ready by the poster submission date. |
| Term 2: Week 12 23rd March – 29th March 2026 | - Made finishing touches to poster and submitted. - Met with supervisor in group meeting and presented progress. | - Poster has been submitted. | - Implementing another model for comparison is proving difficult. I have reached out to my supervisor for assistance. - Less work was completed this week due to other module deadlines. |
| Easter Holiday | - MRI Survey shared with medical imaging team for completion. - Implemented SRDDL as third comparison technique. - Finished writing final report including generating full set of quantitative results, creating diagrams and making visualisations. | - Received responses to the results survey and performed analysis. - All diagrams and visualisations complete. - Final report is complete. | - Results from the survey look very good for my proposed method. - Final touches to final report required before submission. This will require another full read through of the paper. |